# Xolaris LOE — 1-Month Go-Live Plan

Autonomous Security (Xolaris) · 11 September 2026 · 1 engineer · 22 working days (4 weeks)
Engines from the last 3 months stay as-is. This plan only covers hosting, database, and a thin live demo.
Hours are engineering time. GPU rent and Hugging Face download wait are extra.

| 22d This month (working days) | 132h Engineering hours (6h/day) | 4 wk Calendar | Out Wave D / nice-to-have |
| --- | --- | --- | --- |

Why this is 22 days, not 83. The 83-day number was the full leftover backlog (RAG, real execute, extra scanners, OPA, full UI, Alembic, JWT). That work is not in this month. This plan ships a hosted demo: RavenX chat + live Nuclei/Trivy scan + findings stored in Postgres + a locked API. Engines are already written. We host them, we do not rebuild them.

## 1. What “done in 1 month” means

At the end of week 4 a reviewer can:

- Open chat and get an answer from RavenX on the cloud VM (llama.cpp).

- Run a live Nuclei or Trivy scan (not simulate-only).

- See those findings and assets on GET /api/v1/findings and GET /api/v1/assets after a restart (Postgres, not SQLite).

- Call the API with a key (not an open internet API).

- After a plan is created, simulation runs and an approval request is submitted (no real patch on the server).

## 2. Four-week calendar

| Week | Days | Hours | Work | Exit check |
| --- | --- | --- | --- | --- |
| 1 — Host | 5 | 30 | Rent Vast.ai (or RunPod) Linux GPU VM. Download RavenX from Hugging Face. Build llama.cpp on port 8080. Clone backend, pip install, .env, uvicorn. | /chat returns a RavenX answer |
| 2 — Scanners + DB | 5 | 30 | Install Nuclei and Trivy (Prowler/Checkov/Grype only if time). Live scan smoke. Start Postgres 16 from docker-compose. Point DATABASE_URL. Confirm scan writes findings. | Live scan + GET /findings after restart |
| 3 — Persist + test | 6 | 36 | Tenant isolation check. Save chat history in Postgres (replace in-memory MemoryService). E2E happy path: scan → findings → trust → risk → decision → plan. | Restart does not wipe findings or chat |
| 4 — Demo lock | 6 | 36 | Simple API keys. Auto-run simulation and submit approval after a plan. Thin findings list in the existing React app (one page, real API). Rehearse a 10-minute demo. | Keyed API + demo script works |
| Total |  | 22 | 132 hours | Hosted go-live demo |

## 3. Day-by-day LOE (22 days)

| ID | Item | Days | Hours | Cut from the 83-day plan |
| --- | --- | --- | --- | --- |
| W1.1 | Cheap GPU Linux VM (Vast.ai first) | 1.5 | 9 | Was 2d |
| W1.2 | Download RavenX from Hugging Face | 0.5 | 3 | Was 1d; download runs in parallel with VM setup |
| W1.3 | Build llama.cpp and serve on :8080 | 1.5 | 9 | Was 2d |
| W1.4 | Backend clone, venv, requirements, .env, uvicorn | 1.5 | 9 | Was 1d; includes env wiring to llama.cpp |
| W2.1 | Install Nuclei + Trivy on Linux (live PATH) | 2 | 12 | Was 3d; Prowler/Checkov/Grype deferred if time is short |
| W2.2 | Smoke: live scan + chat + GET /findings | 1 | 6 | Same intent, tighter |
| W2.3 | PostgreSQL (existing docker-compose) + DATABASE_URL | 2 | 12 | Was 3d; no Alembic this month (CREATE_TABLES) |
| W3.1 | Multi-tenant check (tenant_id isolation + backup dump) | 1.5 | 9 | Was 3d; indexes/pool hardening later |
| W3.2 | Persistent chat memory in Postgres | 2 | 12 | Was 3d |
| W3.3 | E2E happy path only (scan through plan) | 2.5 | 15 | Was 5d; no full execute/verify/report matrix |
| W4.1 | API keys (not full JWT/OIDC) | 2 | 12 | Was 5d |
| W4.2 | Auto simulation + submit approval after plan | 2.5 | 15 | Was 4d; no auto-execute |
| W4.3 | Findings list page on real API + demo rehearsal | 1.5 | 9 | Was 6d full UI; one screen only |
| Total this month |  | 22 | 132 |  |

## 4. Explicitly out of this month

Do not schedule these in the 22 days. They were most of the old 83-day total.

- Alembic production migrations

- JWT / OIDC / SSO

- Full React wiring (dashboard, pipeline, approvals UX)

- Async scan jobs (GET /scans/{id})

- Live threat feeds (CISA KEV, NVD) and threat-intel REST

- OPA policy transport

- OpenAI / Anthropic providers

- RAG / vector search

- Real execution (SSH/cloud patch) — keep the recording adapter

- Extra scanners: Gitleaks, ZAP, OSV, Semgrep; Prowler/Checkov/Grype live if week 2 slips

- MCP agent tools, nginx TLS polish, structured logging platform

## 5. Already built — do not rebuild

Scan/ingest, adapters (code), normalization, local policy, evidence, assets, findings/assets GET APIs (Feature 4.6), trust, risk, decision, planner, AI harness, simulation, approval, execution orchestration, verification, reporting (Feature 4.5.4), chat V2 to llama.cpp.

HTTP already mounted: POST /scans, GET /findings, GET /assets, trust, risk, decisions, plans, simulations, approvals, executions, verifications, reporting, ai-harness, /chat.

## 6. Microsoft Planner

One feature for this month: 4.7 One-Month Go-Live (22 days).
Keep 4.5 Reporting and 4.6 Findings/Assets complete.
Put the “out of this month” list in a later bucket (4.8 Backlog) with no dates until 4.7 is done.

Assumptions: 1 engineer, 6h/day, 5-day weeks, Vast.ai/RunPod GPU Linux, Nuclei+Trivy as the live scanners, Postgres 16, CREATE_TABLES not Alembic, API keys not SSO. If the GPU VM is delayed, week 1 slips and the month becomes chat-only on simulate scans — call that out immediately.