# Xolaris LOE — Remaining Work after 3 Months

Autonomous Security (Xolaris) · 9 September 2026 · 1 engineer · 6 productive hours/day
Source: docs/architecture modules 0–22, adapter guide, Feature 4.5 Reporting, Feature 4.6 Findings/Assets APIs.
Hours are engineering time only. GPU rental and Hugging Face download wait are extra.

| 3 mo Code already built | 15 Modules done | 10 Partial / not hosted | 83d Remaining person-days |
| --- | --- | --- | --- |

What is left is mostly hosting, not new engines. The control plane is written: Scan → Evidence → Trust → Risk → Decision → Plan → Simulation → Approval → Execution → Verification → Reporting. What is not done is putting RavenX + llama.cpp + scanner binaries + Postgres on a Linux cloud box, then proving the full API path and locking down tenants. Without that, the product only runs in simulate mode on a laptop with SQLite and in-memory chat.

## 1. Delivery mix — code vs production

Share of platform readiness (not lines of code): ~40% production-ready.

- 40% engines/APIs coded

- 25% partial (OPA, threat-intel feeds, live scanners, UI)

- 20% cloud / model / database / memory

- 15% auth, E2E tests, pipeline glue, RAG

Remaining effort: 83 person-days / 490 hours (~17 calendar weeks at 5 days/week, one person).

| Wave | Focus | Days | Hours |
| --- | --- | --- | --- |
| A Host | Cloud + RavenX + llama.cpp + scanners | 10 | 62 |
| B Data | Postgres + memory + E2E | 17 | 96 |
| C Product | Pipeline + auth + UI | 18 | 106 |
| D Later | Intel, RAG, real execute | 38 | 226 |
| Go-live minimum (A + B) |  | 27 | 158 |
| Total remaining |  | 83 | 490 |

## 2. Already built (past 3 months) — do not rebuild

| # | Feature / module | Status | What exists |
| --- | --- | --- | --- |
| 0 | Platform / FastAPI app | Done | Chat, health, CORS, SQLite default |
| 1 | Decision Engine | Partial | Wired to chat; ScanAware router for “scan …”; default still CHAT |
| 2 | Context Manager | Partial | Wired to LLMService V2; RAG builder still empty |
| 3 | Prompt Builder | Partial | Wired; RAG/Agent templates are placeholders |
| 4 | Provider Factory + LlamaProvider | Partial | Llama generate works; OpenAI/Anthropic not implemented |
| 5 | Canonical Security Objects | Done | Findings, evidence, decisions, remediations |
| 6 | Normalization Service | Done | Nuclei, Trivy, Prowler, Checkov, Grype |
| 7 | Policy Engine | Partial | Local rules fail-closed; OPA transport stub |
| 8 | Tool adapters | Partial | Nuclei, Trivy, Prowler, Checkov, Grype code; binaries not hosted |
| 9 | Evidence Repository | Done | Persist, dedupe, search + GET /findings (Feature 4.6) |
| 10 | Asset Inventory | Done | Catalog + GET /assets (Feature 4.6) |
| 11 | Threat Intelligence | Partial | Enrichment services exist; NVD/KEV/MITRE/MISP feeds skipped |
| 12 | Trust Scoring | Done | Deterministic + REST |
| 13 | Risk Engine | Done | Deterministic + REST |
| 14 | Decision Service | Done | Deterministic advisor; AI optional flag off |
| 15 | Remediation Planner | Done | Plans + REST |
| 16 | AI Harness | Done | Governance wrapper + REST |
| 17 | Simulation Engine | Done | Dry-run + REST; not auto-chained after plan |
| 18 | Approval Engine | Done | REST; not auto-submitted after simulation |
| 19 | Execution Engine | Partial | Orchestration done; adapter records success, no real infra |
| 20 | Verification Engine | Done | Post-remediation checks + REST |
| 21 | Reporting & Analytics | Done | Feature 4.5.4 validation/stabilization |
| 22 | Scan / Ingest | Partial | API + simulate path; live needs scanner binaries on Linux |
| 4.6 | Findings & Assets HTTP | Done | Search/get/history; shared store with scan |
| UI | React prototype | Partial | Screens exist; still mock data, not calling FastAPI |

## 3. HTTP already mounted

POST /api/v1/scans · GET /api/v1/findings · GET /api/v1/assets · trust · risk · decisions · remediation-plans · simulations · approvals · executions · verifications · reporting · ai-harness · /chat

Missing HTTP: threat-intel list/get, authenticated user, scan job status, persisted chat sessions.

## 4. Remaining LOE by work item

| ID | Work item | Days | Hours | Why it is still open |
| --- | --- | --- | --- | --- |
| A1 | Cheap GPU Linux cloud (Vast.ai / RunPod / Lambda) | 2 | 12 | Need a Linux box with GPU/RAM to host RavenX. Vast.ai is usually cheapest for hourly GPU. |
| A2 | Download RavenX from Hugging Face | 1 | 6 | Get the GGUF/weights onto the VM disk. Time is mostly download + checksum. |
| A3 | Build and configure llama.cpp server | 2 | 12 | Compile llama.cpp, serve OpenAI-compatible /v1/chat/completions on port 8080. Backend already calls LLAMA_BASE_URL. |
| A4 | Deploy backend + pip install requirements | 1 | 8 | Clone repo, Python venv, requirements.txt, .env (LLAMA_BASE_URL, DATABASE_URL), uvicorn. |
| A5 | Install live scanners on Linux | 3 | 18 | Nuclei, Trivy, Prowler, Checkov, Grype binaries + PATH. Today scans only work in simulate mode without these. |
| A6 | Smoke: live scan + chat to RavenX | 1 | 6 | POST /scans mode=live, /chat against llama.cpp, confirm findings appear on GET /findings. |
| B1 | PostgreSQL instead of SQLite | 3 | 18 | docker-compose.yml already has Postgres 16. Point DATABASE_URL, create DB, CREATE_TABLES or migrations. |
| B2 | Alembic migrations (production schema) | 3 | 16 | CREATE_TABLES is fine for demo; production needs versioned migrations across all engine tables. |
| B3 | Multi-tenant persistent storage hardening | 3 | 16 | Engines already require tenant_id. Left: backups, indexes, connection pool, no SQLite file, isolate tenants in ops. |
| B4 | Persistent chat memory | 3 | 16 | MemoryService is in-RAM (max 20 messages). Restart wipes chat. Store sessions in Postgres per tenant. |
| B5 | End-to-end API testing | 5 | 30 | Full path: scan → findings → trust → risk → decision → plan → simulate → approve → execute → verify → report. Unit tests exist per engine; live E2E does not. |
| C1 | Auto-chain pipeline after Plan | 4 | 24 | FindingPipeline stops at Planner. Simulation, Approval, Execution, Verification exist but must be called separately. |
| C2 | API authentication (JWT or API keys) | 5 | 30 | Every route is open. Needed before any cloud demo on a public IP. |
| C3 | Wire React UI to real APIs | 6 | 36 | Frontend is mock. Replace with GET /findings, /assets, trust, risk, plans, approvals, /chat. |
| C4 | Async scan jobs + GET /scans/{id} | 3 | 16 | Live Nuclei/Trivy can run minutes. Today the HTTP call waits until the scan finishes. |
| D1 | Threat intel REST + one live feed (CISA KEV) | 5 | 30 | Module is placeholder feeds only. No GET /threat-intel. KEV is the smallest real connector. |
| D2 | OPA policy transport | 3 | 16 | Local policy works. OPA backend is fail-closed stub. |
| D3 | OpenAI / Anthropic providers | 2 | 12 | Placeholders. Only Llama/RavenX path works. |
| D4 | RAG / document grounding | 8 | 48 | RAGBuilder returns no documents. Needed for “ask about our findings” with real evidence. |
| D5 | Real execution adapters (cloud/SSH) | 8 | 48 | Execution engine records fake success. Production needs provider adapters without changing orchestration. |
| D6 | Extra scanners (Gitleaks, ZAP, OSV, Semgrep) | 6 | 36 | Adapter guide lists these as next tools. Pattern already exists (~1 day each). |
| D7 | MCP agent tools + logging/HTTPS | 6 | 36 | Docs list get_finding, decide, approve as next MCP tools. Also nginx TLS and structured logs. |

## 5. Wave summaries

### Wave A — go-live host (must) · 10 days · 62 hours

Buy a cheap Linux GPU VM (Vast.ai first, then RunPod if GPUs are scarce). Download RavenX from Hugging Face. Build llama.cpp and serve it on 127.0.0.1:8080. Clone backend, pip install, set LLAMA_BASE_URL and DATABASE_URL. Install Nuclei, Trivy, Prowler, Checkov, Grype. Run one live scan and one chat. Plus GPU rent (~USD 200–500/month if left on).

### Wave B — data that survives restart (must) · 17 days · 96 hours

Switch SQLite to PostgreSQL (compose file already in backend/docker-compose.yml). Add migrations. Confirm tenant_id isolation on findings/assets/trust/risk. Replace in-memory MemoryService with Postgres chat history. Run end-to-end API tests through the whole pipeline.

### Wave C — product (should, after host is up) · 18 days · 106 hours

Auto-run Simulation and submit Approval after a plan. Add login or API keys before the VM is public. Point the React screens at real findings/assets/chat. Make live scans async so Nuclei does not block HTTP.

### Wave D — later (do not start before A+B) · 38 days · 226 hours

Live KEV/NVD threat feeds, OPA, OpenAI/Anthropic fallback, RAG over findings, real patch/SSH execution (today it only records success), extra scanners (Gitleaks, ZAP, OSV), MCP tools, HTTPS and logging.

## 6. Suggested calendar (one engineer)

| Block | When | Days | Outcome |
| --- | --- | --- | --- |
| A Host | Weeks 1–3 | 10 | RavenX answering chat; live Nuclei/Trivy scan writing findings |
| B Data | Weeks 3–6 | 17 | Postgres + tenant storage + chat memory + E2E test pack |
| C Product | Weeks 6–10 | 18 | Pipeline past Plan; auth; UI on real APIs |
| D Later | Weeks 10–16 | 38 | Live intel, RAG, real execute, extra tools |

Planner mapping. Keep Feature 4.5 Reporting and 4.6 Findings/Assets as complete. Next feature bucket should be 4.7 Cloud Hosting (Wave A) then 4.8 Data Plane (Wave B). Do not open Wave D stories until A and B are done — the engines are already written.

Assumptions: 1 engineer; 6h/day; Vast.ai/RunPod GPU Linux; RavenX GGUF served by llama.cpp; scanners installed as OS packages; Postgres 16; no parallel team. Cloud invoice is extra (GPU hourly). Dates are relative to the start of Wave A, not to the 3 months already spent.